CONTRACT

SERVICE CONTRACT FOR EUROPEAN UNION EXTERNAL ACTIONS

PROJECT No. SA-0200142

financed from the general budget of the Union

State Agency for Strategic Programming and Aid Coordination

Street. "Kuvajt", The Embassy of Peace,

Tirana, Albania

M21327452C

(‘the contracting authority’),

of the one part,

and

<Full official name of the contractor>

[<Legal status/title>]

[<Official registration number>]

<Full official address>

[<VAT number>],

(‘the contractor’)

of the other part,

have agreed as follows:

# PROJECT

# "High LEVEL and market-respondent Competences for a Blue and Digitalized “Smart and skilled South Adriatic" – SA SKILLS"

# CONTRACT TITLE

# External Expertise for the Coordination of Work Packages (WP2 and others) and the Facilitation of Blue Economy Activities, including Governance and Policy Harmonisation for the Project "SA Skills", in the Framework of the Interreg IPA South Adriatic Programme 2021-2027

# Identification number SASPAC-SKILLS-SRV-004

(1)	Subject

1.1	The subject of this contract is the provision of specialised external expertise for the coordination of Work Packages, with particular focus on WP2 and related project activities, and the facilitation of Blue Economy activities, including governance, qualification harmonisation, competence framework development, policy mainstreaming, stakeholder coordination, capitalisation and structured content for the SA SKILLS digital platform, in Tirana, Albania and, where relevant, in the South Adriatic programme area, with identification number SASPAC-SKILLS-SRV-004 (“the services”).

1.2	The contractor shall execute the tasks assigned to him in accordance with the terms of reference annexed to the contract (Annex II)

(2)	Contract value

This contract, established in Euro, is a global price contract. The contract value is EUR <amount>, excluding VAT/indirect taxes, where applicable.

(3) 	Entry into force and duration

The start date for implementation shall be the date of signature of the contract by the last party. The period for implementing the tasks shall run until 31 December 2027. Any extension of the implementation period shall be subject to prior written approval and a formal contract amendment, in accordance with the applicable contractual conditions and the approved SA SKILLS project implementation period.

(4)	Order of precedence of contract documents

The following documents shall be deemed to form and be read and construed as part of this contract, in the following order of precedence:

- the contract agreement;

- the special conditions;

- the general conditions (Annex I);

- the terms of reference [including clarification before the deadline for submitting tenders] (Annex II)

- the organisation and methodology [including clarification from the tenderer provided during tender evaluation] (Annex III);

- the Key Expert profile(s) / CV template, where applicable (Annex IV)

- Budget (Annex V);

- forms and other supporting documents, including identification forms, where applicable (Annex VI);

These above listed documents make up the contract. They shall be deemed to be mutually explanatory. In cases of ambiguity or divergence, they shall prevail in the order in which they appear above. Addenda shall have the order of precedence of the document they are amending.

(5)	Language of the contract

The language of the contract and of all written communications between the contractor and the contracting authority and/or the project manager shall be English or in any of official languages of programme participating countries in Latin letter.

(6) 	Payment details

Payments shall be made into the following bank account:

Name of bank: <insert bank name>

Exact denomination of account holder: <insert>

Bank account number/IBAN: <insert>

(7)	Other specific conditions applying to the contract

- The following conditions to the contract shall apply:

For the purpose of Article 42 of the general conditions, for the part of the data transferred by the contracting authority to the European Commission:

(a) the controller for the processing of personal data carried out within the Commission is the head of contracts and finance unit R4 of DG Neighbourhood and Enlargement Negotiations

(b) the data protection notice is available at https://wikis.ec.europa.eu/display/ExactExternalWiki/Annexes#Annexes-AnnexesA(Ch.2):General]

- Done in English in three originals, two originals for the contracting authority and one original for the contractor.

SPECIAL CONDITIONS

These conditions amplify and supplement the general conditions governing the contract. Unless the special conditions provide otherwise, the general conditions remain fully applicable. The numbering of the articles of the special conditions is not consecutive but follows the numbering of the general conditions. Exceptionally, and with the approval of the competent European Commission departments, other clauses can be indicated to cover particular situations.

Article 2	Communications

2.1	All communication related to the contract should be in written, shall state the contract title and identification number, and be submitted to:

For the Contracting Authority:

Mr. Marjus Borokoçi, Legal Representative

State Agency for Strategic Programming and Aid Coordination

Rruga "Kuvajt", 1001, Tirana, Albania

e-mail: marjus.borokoci@saspac.gov.al

For the Contractor:

<Indicate here the contact person, address of the Party, other contact details.>

- Article 7	General obligations

- 7.8	The Contractor must comply with the publicity and visibility requirements of Interreg IPA CBC South Adriatic Programme and the latest Communication and Visibility Requirements for EU-funded external action, laid down and published by the European Commission.

Article 12  Liabilities

12.2 	By way of derogation from Article 12.2, paragraph 2, of the general conditions, compensation for damage resulting from the contractor's liability in respect of the contracting authority is capped at an amount equal to the contract value.

Article 19	Implementation of the tasks and delays

19.1	The start date for implementation shall be date of signature of the contract by the last part.

19.2	The period for implementing the tasks shall run until 31 December 2027. Any extension of the implementation period shall be subject to prior written approval and a formal contract amendment, in accordance with the applicable contractual conditions and the approved SA SKILLS project implementation period.

Article 26	Interim and final reports

The contractor shall submit progress reports as specified in the terms of reference (Annex II).

Article 27	Approval of reports and documents

- 27.5	The contracting authority shall, within 15 days of receipt, notify the contractor of its decision concerning the documents or reports received by it, giving reasons should it reject the reports or documents, or request amendments. If the contracting authority does not give any comments on the documents or reports within the time limit, the contractor may request written acceptance of them. The documents or reports shall be deemed to have been approved by the contracting authority if it does not expressly inform the contractor of any comments within 15 days of the receipt of the report.

Article 29	Payment and interest on late payment

29.1	Payments will be made in accordance with the following the option:

| Month | Payment | Trigger | EUR |
| --- | --- | --- | --- |
| 07/2026 | Maximum.pre-financing /Inception payment | Following contract signature, submission of invoice and approval of the Inception Report | 40 % of the contract value |
| 01/2027 | Interim payment 1 | Following submission of invoice and approval of the first set of deliverables/progress report, as defined in the ToRs and approved work plan | 20 % of the contract value |
| 07/2027 | Interim payment 2 | Following submission of invoice and approval of the second set of deliverables/progress report, as defined in the ToRs and approved work plan | 20 % of the contract value |
| 12/2027 | Balance payment | Following submission of invoice and approval of the Final Technical Report and all final deliverables | 20 % of the contract value |
|  | Total |  | <Total contract value> |

By derogation, the payments to the contractor of the amounts due under inception, interim and final payments shall be made within 90 days after receipt by the contracting authority of an invoice and of the reports, subject to approval of those reports in accordance with Article 27 of the general conditions.

29.5	Payments will be made in Euro in accordance with Articles 20.6 and 29.4 of the general conditions into the bank account notified by the contractor to the contracting authority.

Article 30	Financial guarantee

30.1	Subject to a positive risk assessment by the contracting authority, by derogation from article 30 of the general conditions no pre-financing guarantee is required.

Article 40	Settlement of disputes

40.4	Any disputes arising out of or relating to this contract which cannot be settled otherwise shall be referred to the competent courts of Tirana, Albania, applying the national legislation of the Contracting Authority, unless otherwise provided by the applicable financing agreement.

Article 42	Data protection

1. Processing of personal data related to the implementation of the contract by the contracting authority takes place in accordance with the national legislation of the state of the contracting authority and with the provisions of the respective financing agreement.

2. To the extent that the contract covers an action financed by the European Union, the Contracting Authority may share communications related to the implementation of the contract, with the European Commission. These exchanges shall be made to the Commission, solely for the purpose of allowing the latter to exercise its rights and obligations under the applicable legislative framework and under the financing agreement with the Partner country – contracting authority. The exchanges may involve transfers of personal data (such as names, contact details, signatures and CVs) of natural persons involved in the implementation of the contract (such as contractors, staff, experts, trainees, subcontractors, insurers, guarantors, auditors and legal counsel). In cases where the contractor is processing personal data in the context of the implementation of the contract, he/she shall accordingly inform the data subjects of the possible transmission of their data to the Commission.

When personal data is transmitted to the Commission, the latter processes them in accordance with Regulation (EU) 2018/1725 of the European Parliament and of the Council of 23 October 2018 on the protection of          natural persons with regard to the processing of personal data by the Union institutions, bodies, offices and agencies and on the free movement of such data, and repealing Regulation (EC) No 45/2001 and Decision No 1247/2002/EC and as detailed in the specific privacy statement published at ePRAG.

* * *

- Done in English in three originals, two originals for the contracting authority and one original for the contractor.

| For the contractor |  | For the contracting authority |  |
| --- | --- | --- | --- |
| Name: |  | Name: |  |
| Title: |  | Title: |  |
| Signature: |  | Signature: |  |
| Date: |  | Date: |  |

Where the contracting party is an individual.

Where applicable. For individuals, mention their ID card, passport or equivalent document number.

Except where the contracting party is not VAT registered.

Such risk assessment is required, for example, when a company is awarded a contract without itself meeting the selection criteria but relying on the capacity of another company.

OJ L 205 of 21.11.2018, p. 39.