ANNEX II: TERMS OF REFERENCE

REF: SASPAC-SKILLS-SRV-004

EXTERNAL EXPERTISE FOR THE COORDINATION OF WORK PACKAGES (WP2 AND OTHERS) AND THE FACILITATION OF BLUE ECONOMY ACTIVITIES, INCLUDING GOVERNANCE AND POLICY HARMONISATION FOR THE PROJECT "SA SKILLS", IN THE FRAMEWORK OF THE INTERREG IPA SOUTH ADRIATIC PROGRAMME 2021–2027

TABLE OF CONTENTS

1.	BACKGROUND INFORMATION	4

1.1.	Partner country	4

1.2.	Contracting authority	4

1.3.	Country background	4

1.4.	Current situation in the sector	5

1.5.	Related programmes and other donor activities	5

2.	OBJECTIVES & EXPECTED OUTPUTS	6

2.1.	Overall objective	6

2.2.	Specific objective(s)	6

2.3.	Expected outputs to be achieved by the contractor	6

3.	ASSUMPTIONS & RISKS	8

3.1.	Assumptions underlying the project	8

3.2.	Risks	9

4.	SCOPE OF THE WORK	9

4.1.	General	9

4.1.1.	Description of the assignment	9

4.1.2.	Geographical area to be covered	10

4.1.3.	Target groups	10

4.2. 	Specific work	10

4.2.1.        Methodology and work planning	10

4.2.2.        Comparative analysis of Blue Economy qualifications and professions	11

4.2.3.        Development of a common vocabulary for Blue Economy qualifications and professions	11

4.2.4.        Development of the South Adriatic Blue Competence Framework — BlueComp	11

4.2.5.        Vademecum for integration into mainstreaming programmes	12

4.2.6.        Coordination with EUSAIR and relevant governance structures	12

4.2.7.        Participation in international networks and capitalisation activities	12

4.2.8.        Contribution to the SA SKILLS digital platform	13

4.2.9.        Reporting, quality assurance and final recommendations	13

4.3.	Project management	13

4.3.1.        Responsible body	13

4.3.2.        Management structure	13

4.3.3. Facilities to be provided by the contracting authority and/or other parties	14

5.	LOGISTICS AND TIMING	14

5.1.	Location	14

5.2.	Start date & period of implementation of tasks	14

6.	REQUIREMENTS	15

6.1.	Personnel	15

6.1.1.	Key Expert(s)	15

6.1.2.	Additional experts	17

6.1.3.	Substitution of experts	17

6.2.	Other experts, support facilities & backstopping	17

6.3.	Office accommodation	18

6.4.	Facilities to be provided by the contractor	18

6.5.	Equipment	18

6.6.	Administrative and supporting documentation	18

6.7.	Conflict of interest and professional conduct	19

7.	REPORTING	19

7.1.	Reporting requirements	19

7.2.	Submission and approval of reports	22

8.	MONITORING AND EVALUATION	22

8.1.	Definition of indicators	23

8.1.1.	Timely delivery of outputs	23

8.1.2.	Compliance with the Terms of Reference	23

8.1.3.	Quality of deliverables	23

8.1.4.	Stakeholder coordination and responsiveness	24

8.1.5.	Contribution to project results	24

8.2.	Quality assurance	24

8.3.	Special requirements	25

# BACKGROUND INFORMATION

## Partner country

Albania

## Contracting authority

The contracting authority for this external expertise is State Agency for Strategic Programming and Aid Coordination, as Project Partner 4 (PP4) of the thematic project “High LEVEL and market-respondent Competences for a Blue and Digitalized “Smart and skilled South Adriatic” with Reference No. SA-0200142 – SA SKILLS, financed under Interreg IPA South Adriatic 2021-2027.

## Country background

Albania is located in South-East Europe, in the western part of the Balkan Peninsula. It has a total area of 28,748 square km. The country's border stretches 1,094 km in total, comprising 657 km of land borders, 316 km of maritime boundaries, 48 km of river borders, and 73 km of lake borders. Albania shares land borders with Montenegro to the north, Kosovo to the northeast, North Macedonia to the east, and Greece to the south. To the west, Albania is bordered by the Adriatic Sea, and to the southwest by the Ionian Sea, giving it a strategic coastal position.

According to INSTAT, as of 1 January 2023, the resident population of Albania was estimated at 2,761,785 inhabitants, marking a decrease of 1.1% compared to 1 January 2022. Additionally, data from the September 2023 Census reported 2,402,113 usual residents, showing a sharper decline since the 2011 census. The natural population increase (births minus deaths) in 2023 was 2,331 individuals, an improvement compared to the previous year. However, emigration remains a key demographic challenge, with net migration recorded at 32,497 people in 2022. Albania has been facing population decline since 2001, although this trend varies by region.

Albania's economy is undergoing continuous transformation, moving from a centrally planned system to a market-oriented one. As a potential candidate country for European Union membership, Albania has significant opportunities to enhance its economic performance and alignment with EU standards.

Agriculture and Aquaculture remain vital sectors. According to INSTAT, agriculture (including forestry and fishing) contributes approximately 22.5% to Albania’s GDP (2023), employing over one-third of the workforce. Trade, transport, accommodation, and food services account for about 16.4%, while public administration, education, and health services contribute around 11.5%.

There are around 350,000 agricultural holdings, mainly small, family-run subsistence farms. The average holding is about 1.2 hectares, typically fragmented into 3–5 plots of varying quality.

In aquaculture and fisheries, total catches reached 19,338 tons in 2023, an 8.7% increase over 2022 split roughly equally between capture fisheries and aquaculture (47-48%). Aquaculture production, as per CEIC/INSTAT data, reached 10,011 tons in 2023, up from 8,891 tons in 2022. Inland-water fish farms drove growth (+4,858 t in 2023), with coastal and marine aquaculture also substantial. Aquaculture operations are increasingly concentrated around Vlora, with continued modernization and integration into tourist and export markets.

Sustainable rural development requires a holistic approach: quality healthcare, education, transport, digital infrastructure, employment and income opportunities, vocational training, and climate-resilient services. Investment in infrastructure—roads, energy, water, waste management, and broadband—is essential to make rural and coastal areas desirable and viable. National and regional development strategies must integrate climate change mitigation and adaptation, as well as support for the growing blue-economy, including fishing and aquaculture.

## Current situation in the sector

The South Adriatic regions are facing significant demographic and economic challenges, including high youth and female unemployment, skill mismatches in key sectors, and a general shortage of qualified professionals. The blue economy, which includes traditional maritime industries as well as emerging sectors like blue tourism, digitalization, and biotechnology, presents a major opportunity for economic growth. However, the limited availability of skilled human capital has hindered its development. The region needs structured interventions to ensure better alignment between education, training, and labour market demands.

At present, qualifications often do not reflect the skills required by employers. Many individuals acquire skills informally through work experience yet lack formal recognition. This leads to unemployment and missed opportunities for both businesses and job seekers. Enhancing the education and training system to better respond to market needs is crucial for fostering economic resilience in the South Adriatic.

The region also faces challenges related to brain drain, where skilled professionals seek employment opportunities abroad due to a lack of competitive salaries and career progression in the local market. This trend exacerbates skill shortages and limits the capacity of industries to innovate and grow. Furthermore, the education and vocational training systems often operate in isolation from industry needs, resulting in outdated curricula and a lack of practical training opportunities.

To address these issues, there is a growing need for policy interventions that foster stronger collaboration between the public and private sectors. Enhancing the responsiveness of vocational education and higher education institutions to labour market demands will be critical. Establishing mechanisms for skills forecasting and demand-driven training programs, particularly in the blue economy, can help bridge the gap between education and employment.

Additionally, the lack of comprehensive labour market data and analysis makes it difficult for policymakers to implement evidence-based strategies for workforce development. There is an urgent need for coordinated efforts to improve data collection, facilitate stakeholder dialogue, and implement targeted capacity-building initiatives to support the region’s economic transition and competitiveness.

## Related programmes and other donor activities

This project aligns with the Interreg IPA South Adriatic Programme 2021-2027 and complements other EU-funded initiatives (such as SMART ADRIA, 2B-BLUE, B-VISA 2030, and I-AM_Smart Aquaponics) aimed at strengthening education, employment, and economic cooperation across the region. It builds upon the achievements of previous cross-border projects, leveraging best practices and lessons learned to create a robust framework for stakeholder engagement and skills development.

# OBJECTIVES & EXPECTED OUTPUTS

## Overall objective

The overall objective is to support the harmonisation of Blue Economy qualifications, professions and competence frameworks in the South Adriatic region, through analytical, technical and policy-support services contributing to the development of a common vocabulary, comparative grid, BlueComp framework and mainstreaming recommendations.

## Specific objective(s)

The specific objectives of the assignment are to:

- Develop and apply a common methodology for the comparative analysis of qualification frameworks, professional profiles, training pathways and competence requirements related to the Blue Economy in the South Adriatic region.

- Map and analyse Blue Economy qualifications and professions across the participating territories, identifying similarities, differences, gaps and opportunities for cross-border harmonisation and mutual recognition.

- Define a shared vocabulary and common classification approach for Blue Economy qualifications, competences and professional profiles, ensuring consistency with relevant European frameworks, including the European Qualifications Framework (EQF), where applicable.

- Support the development of the South Adriatic Blue Competence Framework (BlueComp) by identifying key competence areas, skills, knowledge and attitudes relevant to Blue Economy sectors, and by aligning them, where possible, with European competence and qualification principles.

- Provide technical and policy support for the integration of project results into relevant national, regional and macro-regional policy frameworks, including through the preparation of practical recommendations and mainstreaming guidance.

- Facilitate stakeholder coordination and knowledge exchange among project partners, public authorities, education and training institutions, private sector actors and relevant Blue Economy networks, including support to coordination activities with EUSAIR and other relevant initiatives.

- Contribute to the collection and organisation of structured information suitable for inclusion in the project’s digital platform, ensuring consistency with the project outputs and usability for target groups

## Expected outputs to be achieved by the contractor

The Contractor shall deliver the outputs listed below. All deliverables shall be prepared in English, submitted in editable electronic format, and approved by the Contracting Authority before being considered final.

Output 1: Comparative Grid on Blue Qualifications and Professions

Link to project deliverable: D.2.2.1.

Minimum content / requirements: The deliverable shall include a comparative mapping of qualification frameworks, professional profiles, training pathways and competence requirements across the South Adriatic region. The comparative grid shall cover at least 20 qualifications/professional profiles, where sufficient data is available.

Deadline: As defined in the approved Inception Report working plan, in line with the relevant SA SKILLS project deliverable deadline and the contractual implementation period.

Approval authority: The Contracting Authority, represented by the Legal Representative or another person/body formally designated in writing.

Output 2: Technical Report on Common Vocabulary for Blue Economy Qualifications and Professions

Link to project deliverable: D.2.2.1.

Minimum content / requirements: The report shall define a shared terminology and common classification approach for Blue Economy qualifications, competences and professional profiles. It shall include key definitions, descriptors, alignment with relevant EU frameworks, including the European Qualifications Framework (EQF), where applicable, and validation inputs from Project Partners.

Deadline: As defined in the approved Inception Report working plan, in line with the relevant SA SKILLS project deliverable deadline and the contractual implementation period.

Approval authority: The Contracting Authority, represented by the Legal Representative or another person/body formally designated in writing.

Output 3: South Adriatic Blue Competence Framework – BlueComp

Link to project deliverable: D.2.2.2.

Minimum content / requirements: The deliverable shall consist of the BlueComp framework document, identifying key competence areas, knowledge, skills and attitudes relevant to Blue Economy sectors. It shall include key competences structured by categories and, where possible, aligned with EQF levels and relevant EU competence frameworks such as GreenComp and DigComp.

Deadline: As defined in the approved Inception Report working plan, in line with the relevant SA SKILLS project deliverable deadline and the contractual implementation period.

Approval authority: The Contracting Authority, represented by the Legal Representative or another person/body formally designated in writing.

Output 4: Vademecum for Integration into Mainstreaming Programmes

Link to project deliverable: D.2.3.1.

Minimum content / requirements: The Vademecum shall provide practical guidance for integrating project outputs into national, regional and macro-regional programmes. It shall include the mapping of relevant policy frameworks, actionable policy recommendations, and proposed steps for institutional uptake and sustainability.

Deadline: As defined in the approved Inception Report working plan, in line with the relevant SA SKILLS project deliverable deadline and the contractual implementation period.

Approval authority: The Contracting Authority, represented by the Legal Representative or another person/body formally designated in writing.

Output 5: Participation and Report on Coordination with EUSAIR Governance Structures

Link to project deliverable: D.2.3.3.

Minimum content / requirements: The report shall summarize participation and coordination with EUSAIR Pillar 1 – Blue Growth Coordinators, the Thematic Steering Group or other relevant governance structures. It shall include key inputs, conclusions and relevance for project implementation and capitalisation.

Deadline: As defined in the approved Inception Report working plan, in line with the relevant SA SKILLS project deliverable deadline and the contractual implementation period.

Approval authority: The Contracting Authority, represented by the Legal Representative or another person/body formally designated in writing.

Output 6: Report on Participation in International Networks

Link to project deliverable: Related to WP2/WP3 capitalisation and networking activities.

Minimum content / requirements: The report shall include a list of relevant Blue Economy, skills, education or innovation networks; a summary of participation or contribution to relevant events and initiatives; and recommendations for further networking and capitalisation of SA SKILLS results.

Deadline: As defined in the approved Inception Report working plan, in line with the relevant SA SKILLS project deliverable deadline and the contractual implementation period.

Approval authority: The Contracting Authority, represented by the Legal Representative or another person/body formally designated in writing.

Output 7: Digital Platform Content Package

Link to project output: Related to SA SKILLS digital platform activities.

Minimum content / requirements: The deliverable shall include structured content and data inputs for the Blue Economy digital platform, based on the outputs produced under this assignment. The Contractor shall provide content suitable for upload and use by the responsible platform manager/expert. The Contractor shall not be responsible for the technical development, hosting, maintenance or administration of the digital platform, unless expressly provided elsewhere in the contract.

Deadline: As defined in the approved Inception Report working plan, in line with the relevant SA SKILLS project deliverable deadline and the contractual implementation period.

Approval authority: The Contracting Authority, represented by the Legal Representative or another person/body formally designated in writing.

Note: The exact timetable for the preparation, submission, review and final approval of each output shall be established in the detailed work plan submitted as part of the Inception Report. Once approved by the Contracting Authority, the Inception Report and its work plan shall constitute the operational basis for monitoring the timely delivery of the assignment. The work plan shall be consistent with the SA SKILLS project implementation calendar, the deadlines of the corresponding project deliverables, the payment milestones provided in Article 29 of the Special Conditions, and the overall contractual implementation period.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

- Strong cooperation and information-sharing between the contractor, Lead Partner and project partners.

- Exchange of documentation among project partners to ensure a  cross-border evaluation in the reports and document to be issued

## Risks

- Lack of information available at national and cross-border level

- Poor communication and coordination between partners.

- Delays in the project activities implementation

The Contractor shall address these risks through early data requests, regular coordination with the Contracting Authority and Project Partners, use of alternative public sources where appropriate, timely escalation of delays and inclusion of appropriate risk-mitigation measures in the Inception Report.

# SCOPE OF THE WORK

## General

## Description of the assignment

The assignment concerns the provision of specialized external expertise to support SASPAC, as Project Partner 4 under the SA SKILLS project, in the implementation of activities related to Blue Economy governance, qualification harmonisation, competence framework development, policy mainstreaming and stakeholder coordination.

The Contractor shall support the Contracting Authority in developing analytical, technical and policy-oriented outputs contributing to the harmonisation of education, training and professional systems in the Blue Economy sector across the South Adriatic region. The assignment shall contribute to the development of a common understanding of Blue Economy qualifications and professions, the identification of emerging skills and job profiles, the preparation of the South Adriatic Blue Competence Framework — BlueComp — and the integration of project results into relevant policy and governance frameworks.

The services shall be implemented through a results-oriented and participatory approach, ensuring regular coordination with SASPAC, the Lead Partner, Project Partners and relevant stakeholders. The Contractor shall ensure that all outputs are technically sound, evidence-based, practical, and suitable for institutional use, policy uptake, dissemination and capitalisation within the SA SKILLS project.

In particular, the Contractor shall support the following areas of work:

- comparative analysis and harmonisation of Blue Economy qualifications and professions;

- development of a shared vocabulary and common classification approach for Blue Economy qualifications, competences and professional profiles;

- preparation of the South Adriatic Blue Competence Framework — BlueComp;

- preparation of practical guidance for the integration of project results into mainstreaming programmes and policy frameworks;

- participation, coordination and knowledge exchange with relevant governance structures, including EUSAIR Pillar 1 — Blue Growth, where applicable;

- contribute to the collection and organisation of structured information suitable for inclusion in the project’s digital platform, ensuring consistency with the project outputs and usability for target groups

- preparation of technical reports, meeting documents, policy recommendations and final reporting.

The Contractor shall perform the assignment in close cooperation with the Contracting Authority and shall obtain the necessary approvals before finalising the deliverables foreseen under this contract.

## Geographical area to be covered

The main place of implementation shall be Tirana, Albania.

However, considering the cross-border nature of the SA SKILLS project, the assignment shall cover, through desk research, partner inputs, online coordination and, where relevant, participation in project activities, the South Adriatic programme area, including Albania, Montenegro and the Italian partner regions involved in the project.

The Contractor shall take into account the transnational and cross-border dimension of the project when preparing analyses, comparative grids, policy recommendations, competence frameworks and other deliverables.

## Target groups

The primary target groups of the assignment shall include:

- national, regional and local public authorities responsible for education, training, employment, labour market policies, Blue Economy sectors, regional development and innovation;

- education and training institutions, including vocational education and training providers, universities, research centres, laboratories and competence centres active in Blue Economy-related fields;

- private sector actors, including SMEs, start-ups, business associations and operators active in traditional and emerging Blue Economy sectors;

- public and private stakeholders involved in fisheries, aquaculture, maritime transport, coastal and maritime tourism, marine renewable energy, digitalization, biotechnology and other Blue Economy-related sectors;

- Project Partners and associated stakeholders of the SA SKILLS project;

- macro-regional and cross-border cooperation structures, including relevant EUSAIR governance structures, networks and thematic platforms.

## 4.2. 	Specific work

The contractor shall carry out the following tasks:

## 4.2.1.   Methodology and work planning

The Contractor shall prepare and submit an inception report setting out the proposed methodology, detailed work plan, timetable, coordination arrangements, data collection tools and risk mitigation measures.

The methodology shall explain how the Contractor intends to collect, compare, validate and structure information from Project Partners and relevant stakeholders. It shall also define the approach to be used for the preparation of the comparative grid, common vocabulary, BlueComp framework, mainstreaming vademecum, and coordination reports.

The methodology shall be discussed with and approved by the Contracting Authority before the full implementation of the assignment.

## 4.2.2.    Comparative analysis of Blue Economy qualifications and professions

The Contractor shall collect, review and analyse relevant information on qualification frameworks, professional profiles, training pathways, occupational standards, competence requirements and labour market needs related to Blue Economy sectors in the South Adriatic region.

The analysis shall include, where data is available, a minimum of 20 qualifications and/or professional profiles relevant to the Blue Economy. The Contractor shall identify similarities, differences, gaps and opportunities for harmonisation across the participating territories.

The Contractor shall prepare a comparative grid presenting the collected information in a structured and comparable format. The grid shall support cross-border understanding, mutual learning and possible future alignment of qualifications, professional profiles and competence requirements.

## 4.2.3.    Development of a common vocabulary for Blue Economy qualifications and professions

The Contractor shall analyse existing terminology used by Project Partners, institutions and relevant frameworks to describe Blue Economy professions, qualifications, competences, skills and training pathways.

Based on this analysis, the Contractor shall develop a shared vocabulary and common classification approach for Blue Economy qualifications and professional profiles. The vocabulary shall include key terms, definitions and descriptors, and shall seek alignment, where appropriate, with European frameworks such as the European Qualifications Framework.

The Contractor shall ensure that the common vocabulary is clear, practical and suitable for use in project outputs, policy documents, stakeholder consultations and digital dissemination tools.

## 4.2.4.    Development of the South Adriatic Blue Competence Framework — BlueComp

The Contractor shall contribute to the design and preparation of the South Adriatic Blue Competence Framework — BlueComp — as a reference framework for Blue Economy competences in the South Adriatic region.

The Contractor shall review relevant European competence and qualification frameworks, including, where applicable, EQF, GreenComp, DigComp and other relevant EU or sectoral references. Based on this review, the Contractor shall identify and structure key competence areas relevant to Blue Economy sectors.

The BlueComp framework shall include a minimum of 15 key competences, structured by categories and described in terms of knowledge, skills and attitudes, where appropriate. The framework shall also indicate possible links with qualification levels, training pathways and professional profiles, where such links can be reasonably established.

The Contractor shall collect and integrate feedback from the Contracting Authority, Project Partners and relevant stakeholders before finalising the framework.

## 4.2.5.    Vademecum for integration into mainstreaming programmes

The Contractor shall prepare a Vademecum providing practical guidance for the integration of SA SKILLS project outputs into national, regional and macro-regional programmes, strategies and institutional frameworks.

The Vademecum shall identify relevant policy and programme frameworks and propose practical steps for the uptake, transfer and sustainability of the project results. It shall include a minimum of 10 actionable policy recommendations, addressed to relevant institutions and stakeholders.

The document shall be concise, operational and suitable for use by public authorities, education and training institutions, Project Partners and other stakeholders involved in Blue Economy skills development and governance.

## 4.2.6.    Coordination with EUSAIR and relevant governance structures

The Contractor shall support coordination and knowledge exchange with relevant macro-regional and governance structures, including EUSAIR Pillar 1 — Blue Growth Coordinators, the Thematic Steering Group and other relevant initiatives, where applicable and in line with the approved work plan.

The Contractor shall participate in relevant meetings or coordination activities, collect and analyse inputs relevant to the SA SKILLS project, and prepare a report summarizing the main outcomes, conclusions and implications for project implementation, capitalisation and policy alignment.

The Contractor shall ensure that findings from these coordination activities are reflected, where appropriate, in the project deliverables.

## 4.2.7.    Participation in international networks and capitalisation activities

The Contractor shall support the identification of relevant Blue Economy, education, skills, innovation and regional cooperation networks that may contribute to the visibility, transfer and capitalisation of SA SKILLS results.

The Contractor shall prepare a structured overview of relevant networks and, where applicable, support the preparation of project contributions to international events, thematic sessions or knowledge exchange activities.

The Contractor shall prepare a report summarizing relevant networking activities, key contacts, lessons learned and recommendations for further capitalisation of project results.

## 4.2.8.    Contribution to the SA SKILLS digital platform

The Contractor shall provide structured content and data inputs for the SA SKILLS digital platform, based on the outputs produced under this assignment.

The content shall be clear, consistent, comparable and suitable for digital use. It may include summaries of qualifications, professional profiles, competence areas, vocabulary entries, policy recommendations and other relevant materials.

The Contractor shall coordinate with the Contracting Authority and the responsible platform partner or platform manager to ensure that the content is provided in the required format. Unless otherwise agreed, the Contractor shall not be responsible for software development, platform maintenance or technical hosting.

## 4.2.9.    Reporting, quality assurance and final recommendations

The Contractor shall prepare all reports and deliverables foreseen under the contract in accordance with the approved methodology, work plan and deadlines.

All outputs shall be prepared in English and submitted in editable electronic format. The Contractor shall ensure that all deliverables are clear, coherent, technically sound, evidence-based and suitable for institutional and policy use.

The Contractor shall integrate comments received from the Contracting Authority and, where relevant, from Project Partners. Final deliverables shall be considered accepted only after formal approval by the Contracting Authority.

At the end of the assignment, the Contractor shall submit a Final Technical Report summarizing the activities performed, deliverables produced, results achieved, difficulties encountered, mitigation measures, lessons learned, policy recommendations and proposed future actions.

## Project management

## 4.3.1.    Responsible body

The responsible body for the implementation and management of this contract shall be the State Agency for Strategic Programming and Aid Coordination (SASPAC), acting as Project Partner 4 under the SA SKILLS project.

## 4.3.2.    Management structure

The Contractor shall implement the assignment under the overall supervision of the Legal Representative and the Internal Management Team appointed by SASPAC for the SA SKILLS project.

The Contractor shall maintain regular communication with the Contracting Authority and shall coordinate with the Lead Partner, Project Partners and relevant stakeholders whenever required for the successful implementation of the assignment.

The Contractor shall not make commitments, represent the Contracting Authority, modify the work plan, approve project outputs, extend deadlines or take decisions affecting the implementation of the contract without the prior approval of the Contracting Authority.

The Contracting Authority shall review and approve the deliverables submitted by the Contractor in accordance with the procedures and deadlines established in the contract

## 4.3.3.    Facilities to be provided by the contracting authority and/or other parties

The Contracting Authority shall provide the Contractor with access to relevant project documents, available information, templates, contact points and coordination channels necessary for the implementation of the assignment.

The Contractor shall be responsible for its own office accommodation, equipment, communication tools, administrative support and any other resources required to perform the services, unless otherwise expressly provided in the contract.

The Contracting Authority may facilitate communication with Project Partners and stakeholders, but the Contractor shall remain responsible for timely follow-up, preparation of technical materials and delivery of the outputs foreseen under this assignment.

# LOGISTICS AND TIMING

## Location

The main place of implementation of the assignment shall be Tirana, Albania, at the premises of the Contracting Authority and/or other locations designated by the Contracting Authority, where relevant.

Considering the cross-border nature of the SA SKILLS project, the Contractor may also be required to participate in meetings, consultations or coordination activities involving Project Partners and stakeholders from the South Adriatic programme area. Such participation may take place in person, online or in hybrid format, depending on the needs of the project and the approved work plan.

All travel, accommodation, subsistence and logistical costs necessary for the implementation of the assignment shall be deemed to be included in the Contractor’s financial offer, unless expressly provided otherwise in the Special Conditions.

Participation in meetings outside Tirana shall be carried out only where necessary for the implementation of the assignment and subject to prior approval by the Contracting Authority.

## Start date & period of implementation of tasks

The intended start date is July 2026 and the period of implementation of the contract will be from the contract signature by the last party until 31 December 2027. Please refer to Articles 19.1 and 19.2 of the Special Conditions for the actual start date and period of implementation. Any extension of the implementation period shall be subject to prior written approval and a formal contract amendment, in accordance with the applicable contractual conditions and the approved project implementation period.

# REQUIREMENTS

## Personnel

The Contractor shall ensure the availability of qualified personnel with the necessary technical expertise, professional experience and operational capacity to perform the services described in these Terms of Reference.

The tenderer may be either a natural person or a legal person. In both cases, the tenderer shall propose the expert or team of experts responsible for the implementation of the assignment. The technical capacity of the tenderer shall be assessed on the basis of the qualifications, professional experience and suitability of the proposed expert(s), as well as the proposed methodology and organisation of the work.

The proposed expert(s) shall be available for the implementation of the assignment throughout the contractual period and shall perform the services in accordance with the approved work plan, reporting requirements and instructions of the Contracting Authority.

Please note that civil servants and other staff members of the public administration of the partner country, or of international/regional organisations based in that country, may be proposed as experts only where permitted under the applicable rules and duly justified. The tenderer shall provide evidence demonstrating the expert’s availability, absence of conflict of interest, and, where applicable, secondment or leave arrangements. Approval shall remain subject to the assessment of the Contracting Authority in accordance with PRAG and the applicable contractual provisions.

## Key Expert(s)

The tenderer (hereinafter referred to as the Contractor) may be either a natural person (individual consultant) or a legal person (company or consultancy).

In all cases, the Contractor shall propose at least one Key Expert responsible for the technical implementation, coordination and quality assurance of the assignment.

The Key Expert shall have the profile described below.

Education

The Key Expert shall have a university degree, preferably at Master’s level or equivalent, in a field relevant to the assignment, such as:

- economics;

- education or vocational education and training;

- social sciences;

- public policy or public administration;

- labour market studies or human capital development;

- maritime studies or Blue Economy-related fields;

- law;

- regional development;

- another field directly relevant to the scope of the assignment.

In the absence of a relevant university degree, at least 3 (three) additional years of relevant professional experience may be accepted.

General professional experience

The Key Expert shall have at least 5 (five) years of relevant professional experience in one or more of the following areas:

- Blue Economy, maritime sectors or sectoral development;

- skills development and qualification frameworks;

- education and training systems, including vocational education and training;

- labour market analysis and competence mapping;

- policy development, governance and institutional coordination;

- regional development and cross-border cooperation;

- institutional capacity building;

- research, analytical work and preparation of policy-oriented reports.

Specific professional experience

The Key Expert shall demonstrate proven experience in at least 1 (one) of the following areas:

- implementation of EU-funded or international cooperation projects, preferably Interreg, IPA or comparable multi-partner programmes;

- development or analysis of qualification frameworks, occupational standards, competence models or professional profiles;

- preparation of analytical studies, territorial analyses, comparative assessments or policy reports;

- labour market analysis, skills intelligence, competence mapping or identification of emerging professions;

- cooperation with public institutions, education and training providers, universities, research centres, SMEs or other relevant stakeholders;

- policy support, governance processes or integration of project results into public programmes and institutional frameworks;

- participation in international networks, platforms or initiatives related to skills, education, employment, Blue Economy or regional cooperation;

Experience with the European Qualifications Framework, GreenComp, DigComp, EUSAIR, the Adriatic-Ionian region, the South Adriatic area or similar cross-border cooperation contexts shall be considered an asset.

Skills and competences

The Key Expert shall demonstrate the ability to:

- coordinate multidisciplinary and cross-border activities;

- engage with institutional and non-institutional stakeholders;

- facilitate consultations, meetings and knowledge exchange activities;

- analyse complex information and present it in a structured and practical manner;

- produce high-quality technical reports, policy recommendations and operational guidance documents;

- work effectively in English, both written and spoken;

- ensure timely delivery and quality control of all outputs.

## Additional experts

The Contractor may propose additional experts or support staff where necessary for the successful implementation of the assignment.

Additional experts may cover complementary fields such as Blue Economy sectors, vocational education and training, labour market analysis, policy mainstreaming, stakeholder facilitation, data structuring, event facilitation or communication.

The costs of additional experts, support staff, backstopping, administrative support and any other human resources required for the implementation of the assignment shall be deemed to be included in the Contractor’s financial offer.

Unless expressly required in the tender dossier, CVs of non-key experts shall not be submitted or evaluated. However, the tenderer shall clearly demonstrate in the organisation and methodology section that it has access to the necessary expertise and resources to perform the assignment.

## Substitution of experts

The Contractor shall implement the assignment with the expert(s) proposed in the tender and accepted by the Contracting Authority.

Any replacement of the Key Expert(s) shall be subject to prior written approval by the Contracting Authority. The proposed replacement expert shall have qualifications and professional experience at least equivalent to those of the expert originally proposed and accepted. Replacement shall not result in any reduction of the quality of services and shall be governed by the applicable General and Special Conditions of the service contract.

The Contractor shall ensure continuity of implementation and shall bear any additional costs resulting from the replacement of experts.

## Other experts, support facilities & backstopping

The Contractor shall be responsible for providing all technical, administrative and logistical support necessary for the proper implementation of the assignment.

The Contractor shall ensure that the Key Expert and any additional experts are adequately supported in relation to:

- data collection and document review;

- coordination with Project Partners and stakeholders;

- preparation of deliverables and reports;

- organisation and facilitation of technical meetings;

- quality assurance and internal review of outputs;

- communication with the Contracting Authority.

The Contractor shall ensure sufficient backstopping capacity to guarantee timely delivery, continuity of services and quality control throughout the implementation period.

All costs related to support facilities, backstopping, administrative assistance, communication tools, interpretation or translation support, where necessary, shall be included in the financial offer, unless otherwise expressly provided in the contract.

## Office accommodation

The Contractor shall be responsible for providing its own office accommodation and working facilities required for the implementation of the assignment.

The Contractor shall ensure that the expert(s) are accessible during normal working hours by telephone, email and online communication tools. The Contractor shall also ensure availability for in-person meetings in Tirana when required by the Contracting Authority and agreed in the approved work plan.

No office accommodation shall be provided by the Contracting Authority, unless otherwise expressly agreed.

## Facilities to be provided by the contractor

The Contractor shall provide all facilities, equipment and resources necessary to perform the services under the contract, including but not limited to:

- computers, software and office equipment;

- internet access and communication tools;

- online meeting facilities;

- administrative and technical support;

- tools for data collection, analysis and reporting;

- document preparation and editing facilities;

- any other resources necessary for the timely and professional delivery of the assignment.

The Contractor shall ensure that all outputs are prepared in a professional format, in English, and submitted in editable electronic format, unless otherwise requested by the Contracting Authority.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

## Administrative and supporting documentation

The tenderer shall submit the documentation required by the tender dossier to demonstrate compliance with the minimum requirements of this assignment.

The documentation may include, where applicable:

- curriculum vitae of the proposed Key Expert(s);

- copy of academic diploma or equivalent evidence of education;

- evidence of relevant professional experience, such as certificates, references, contracts or other supporting documents;

- evidence of experience in EU-funded, international or cross-border projects, where relevant;

- declaration confirming the availability of the proposed Key Expert(s) for the implementation of the assignment;

- declaration that the tenderer and proposed expert(s) are not in a situation of conflict of interest;

- documents proving the legal establishment of the tenderer, in the case of a legal person;

- declaration on honor or other exclusion/selection documents required under the applicable PRAG tender dossier.

The set of documents shall begin with a self-declaration, listing the documentation submitted. Supporting documents shall be submitted in the form required by the tender dossier. This self-declaration must be duly signed and, where applicable, stamped.

The Contracting Authority may request clarifications or additional certified/notarized document copies only where necessary and in accordance with the applicable procurement rules.

The tenderer shall ensure that all information submitted is accurate, complete and verifiable. Any false, misleading or incomplete information may lead to rejection of the tender or other consequences provided under the applicable rules.

## Conflict of interest and professional conduct

The Contractor and its expert(s) shall perform the assignment with professional independence, impartiality and integrity.

The Contractor shall immediately inform the Contracting Authority of any actual or potential conflict of interest that may arise during the procurement procedure or during implementation of the contract.

The Contractor and its expert(s) shall not use their position to obtain any unauthorized advantage and shall not undertake any activity that may compromise the impartial and professional implementation of the assignment.

The Contractor shall comply with the applicable PRAG rules, contractual provisions and ethical standards throughout the implementation of the contract.

# REPORTING

## Reporting requirements

The Contractor shall prepare and submit all reports and deliverables required under these Terms of Reference in accordance with the approved work plan, the contractual deadlines and the instructions of the Contracting Authority.

All reports shall be prepared in English, submitted in editable electronic format, and accompanied by any relevant annexes, supporting documents, datasets, meeting materials or other evidence of work performed, where applicable.

The Contractor shall ensure that all reports are clear, complete, technically sound, evidence-based and suitable for institutional use, project reporting, policy follow-up, dissemination and capitalisation purposes.

The following reports shall be submitted:

Inception Report

The Contractor shall submit an Inception Report within 10 calendar days from the start of implementation of the contract.

The Inception Report shall include, at minimum:

- proposed methodology for the implementation of the assignment;

- detailed work plan and timetable for the implementation of all activities and outputs;

- for each contractual output, the planned activities, responsible expert(s), data collection and consultation steps, draft submission date, review period, final submission date, link to the relevant SA SKILLS project deliverable and corresponding payment milestone;

- description of the coordination arrangements with the Contracting Authority, Lead Partner, Project Partners and relevant stakeholders;

- proposed data collection and validation approach, including the tools and sources to be used for collecting, comparing and validating information;

- list of documents, information and inputs required from Project Partners and other relevant stakeholders;

- proposed structure of the main deliverables, including the comparative grid, common vocabulary, BlueComp framework, mainstreaming Vademecum, coordination reports and digital platform content package;

- initial risk assessment and mitigation measures, including risks related to delays, availability of data, stakeholder coordination and approval of deliverables;

- any clarifications or operational issues requiring confirmation by the Contracting Authority.

The Inception Report shall be reviewed and approved by the Contracting Authority. Once approved, the Inception Report, including its detailed work plan and timetable, shall serve as the operational basis for the implementation, monitoring, coordination and approval of all activities and deliverables under the contract. The approved work plan shall be consistent with the SA SKILLS project implementation schedule, the relevant project deliverable deadlines, the payment milestones provided in Article 29 of the Special Conditions, and the overall contractual implementation period.

Technical deliverables and progress reporting

The Contractor shall submit the technical deliverables foreseen under Section 2.3 of these Terms of Reference in accordance with the approved work plan and the deadlines agreed with the Contracting Authority.

Depending on the implementation schedule, the Contracting Authority may request short progress updates or coordination notes to monitor the status of activities, including:

- progress achieved against the approved work plan;

- activities completed during the reporting period;

- deliverables under preparation;

- consultations or meetings held with Project Partners and stakeholders;

- difficulties encountered and proposed corrective measures;

- risks affecting timely delivery;

- next steps and upcoming deadlines.

Progress updates may be submitted by email, in meeting notes or in another format agreed with the Contracting Authority. They shall not replace the formal technical deliverables required under the contract.

Interim Report

The Contractor shall submit an Interim Report at a stage agreed in the approved work plan and, where applicable, linked to the relevant interim payment foreseen in Article 29 of the Special Conditions.

The Interim Report shall provide a consolidated overview of implementation progress and shall include, at minimum:

- summary of activities carried out up to the reporting date;

- status of deliverables submitted, under review or pending;

- key findings emerging from the comparative analysis, vocabulary development, BlueComp framework, mainstreaming work or other technical activities;

- summary of coordination with the Contracting Authority, Lead Partner, Project Partners and relevant stakeholders;

- overview of meetings, consultations, workshops or coordination activities carried out;

- difficulties encountered and measures taken or proposed to address them;

- updated risk assessment, where relevant;

- updated work plan for the remaining period of implementation;

- annexes containing relevant technical outputs, meeting materials, attendance lists, datasets or other supporting documents, where applicable.

The Interim Report shall be submitted in editable electronic format and shall be subject to review and approval by the Contracting Authority.

Final Technical Report

The Contractor shall submit a Final Technical Report within 15 calendar days after completion of all assignment activities and before submission of the final invoice.

The Final Technical Report shall include, at minimum:

- summary of all activities performed under the contract;

- list and description of all deliverables produced;

- results achieved in relation to the objectives of the assignment;

- summary of consultations, meetings and coordination activities carried out;

- main findings, conclusions and policy recommendations;

- contribution of the assignment to the SA SKILLS project outputs;

- difficulties encountered and mitigation measures applied;

- lessons learned and recommendations for further action;

- confirmation of finalisation and submission of all approved deliverables;

- annexes containing the final versions of deliverables, meeting reports, supporting materials and other relevant documents, where applicable.

The Final Technical Report shall be submitted together with the final invoice and shall be subject to approval by the Contracting Authority before the final payment is authorized.

## Submission and approval of reports

All reports and deliverables shall be submitted to the Contracting Authority, represented by the Legal Representative of SASPAC as Project Partner 4, or to another contact point formally designated by the Contracting Authority.

Reports and deliverables shall be submitted in editable electronic format, unless hard copies are specifically requested by the Contracting Authority. Where hard copies are required, the number of copies shall be specified by the Contracting Authority.

The Contracting Authority shall review each report or deliverable and may:

- approve it without comments;

- approve it subject to minor corrections;

- request revisions, clarifications or additional information;

- reject it if it does not comply with the Terms of Reference, the approved methodology, the contractual requirements or the quality standards expected under the assignment.

Where comments or requests for revision are provided, the Contractor shall revise and resubmit the report or deliverable within the deadline indicated by the Contracting Authority. Unless otherwise agreed, revised versions shall be submitted within 7 calendar days from receipt of comments.

A report or deliverable shall be considered accepted only after written approval by the Contracting Authority. Acceptance of reports and deliverables shall be a condition for the authorization of the relevant payment, where applicable.

The Contractor shall ensure that all reports, deliverables and supporting materials are properly archived and made available to the Contracting Authority upon request throughout the implementation period of the contract.

# MONITORING AND EVALUATION

## Definition of indicators

The implementation of the assignment shall be monitored by the Contracting Authority throughout the duration of the contract, in order to ensure that the services are delivered in accordance with these Terms of Reference, the approved work plan, the contractual provisions and the objectives of the SA SKILLS project.

Monitoring shall be carried out by the Legal Representative and/or the Internal Management Team of SASPAC as Project Partner 4, based on the review of deliverables, progress updates, meetings, consultations and other evidence of work performed by the Contractor.

The performance of the Contractor shall be assessed on the basis of both qualitative and quantitative indicators, including but not limited to the following:

## Timely delivery of outputs

The Contractor shall submit all reports, technical deliverables and supporting materials within the deadlines established in the approved work plan and the contract.

The following aspects shall be monitored:

- submission of the Inception Report within the required deadline;

- timely submission of all technical deliverables listed under Section 2.3;

- timely organisation or support to meetings and coordination activities;

- timely submission of revised versions following comments from the Contracting Authority;

- timely submission of the Final Technical Report and related annexes.

## Compliance with the Terms of Reference

The Contractor’s performance shall be assessed against the scope, objectives, tasks and deliverables defined in these Terms of Reference.

The following aspects shall be monitored:

- consistency of the services with the overall and specific objectives of the assignment;

- completion of all tasks foreseen under Section 4;

- delivery of all outputs foreseen under Section 2.3;

- compliance with the approved methodology and work plan;

- respect of contractual requirements, reporting obligations and approval procedures.

## Quality of deliverables

The Contracting Authority shall assess the quality, relevance and usability of the outputs produced by the Contractor.

The following aspects shall be monitored:

- technical soundness and accuracy of the analysis;

- clarity and coherence of the reports and deliverables;

- evidence-based conclusions and recommendations;

- practical relevance for the SA SKILLS project and its target groups;

- consistency with relevant EU frameworks, where applicable;

- suitability of outputs for institutional use, policy uptake, dissemination and capitalisation;

- professional formatting, structure and language quality;

- incorporation of comments received from the Contracting Authority and, where relevant, from Project Partners.

## Stakeholder coordination and responsiveness

The Contractor shall maintain effective communication and coordination with the Contracting Authority, Lead Partner, Project Partners and relevant stakeholders.

The following aspects shall be monitored:

- responsiveness to requests for information, clarification or revision;

- regular communication with the Contracting Authority;

- effective coordination with Project Partners for data collection and validation;

- ability to facilitate consultations, meetings and stakeholder exchanges;

- constructive approach to problem-solving and adaptation to project needs;

- timely reporting of difficulties, risks or delays affecting implementation.

## Contribution to project results

The Contractor’s contribution shall also be assessed in relation to the expected results of the SA SKILLS project.

The following aspects shall be monitored:

- contribution to the harmonisation of Blue Economy qualifications and professions;

- contribution to the development of the common vocabulary and comparative grid;

- contribution to the preparation of the BlueComp framework;

- contribution to policy mainstreaming and institutional uptake of project results;

- contribution to coordination with EUSAIR and relevant networks;

- contribution to the update of the project’s digital platform;

## Quality assurance

The Contractor shall establish and apply internal quality assurance procedures to ensure the accuracy, consistency and professional quality of all deliverables.

The Contractor shall ensure that:

- all deliverables are reviewed internally before submission;

- data and information used in the analysis are reliable and properly referenced;

- conclusions and recommendations are supported by evidence;

- deliverables are coherent with one another and with the objectives of the assignment;

- terminology is used consistently across all outputs;

- comments from the Contracting Authority and Project Partners are duly considered and incorporated where appropriate.

The Contractor shall remain responsible for the quality of all outputs submitted under the contract, including outputs prepared with the support of additional experts or support staff.

## Special requirements

The Contractor shall comply with all applicable contractual, ethical and professional obligations during the implementation of the assignment.

The Contractor shall ensure confidentiality of all documents, data and information received from the Contracting Authority, Project Partners or stakeholders, unless such information is already public or its disclosure has been authorized by the Contracting Authority.

All materials produced under the contract shall be prepared in accordance with the visibility, communication and branding requirements applicable to the SA SKILLS project and the Interreg IPA South Adriatic Programme 2021–2027, where relevant.

Unless otherwise provided in the contract, no special requirements shall apply.

* * *